## README
VELOOP REWARDS - Task 01 ¦ Work Package N: Developer Analytics Handoff
Every requirement is Proposed or To Be Verified. No event is claimed to exist in VELOOP; Implementation status is 'To be confirmed by Engineering'. No simulated or real VELOOP statistics are included.
How to use: read General_Requirements and Preconditions first, then Event_Requirements (one row per event) with its Payload_Fields. Engineers fill the 'Engineering response' and 'Engineering owner' columns.
Scope: all Critical and High priority events from the Event Tracking Plan. Medium and Low events follow the same pattern and can be specified when needed.
Open questions:
- Which of these events exist today, and which service would emit each? (A001, A011)
- Which approved lists (statuses, units, methods, categories) will be used? (A002, A006)
- Which idempotency design will be used for wallet and event writes? (A005)
- What retry and queue approach is acceptable for undelivered events?
- Which onboarding steps, account statuses and failure categories are real? (A003, A019)
Live counts
Event requirements | 25
Critical events | 9
High events | 16
Payload field rows | 120
General requirements | 12
Pre-conditions | 12

## Event_Requirements
Requirement ID | Event | Priority | Trigger | Definition | Source | Timestamp | Deduplication | Event rules (validation) | Why needed | KPI dependency | Acceptance test (positive) | Acceptance test (negative) | Status | Notes | Implementation status | Engineering response | Engineering owner
AE-001 | user_registered | Critical | Account creation succeeds | A new user account has been created | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | user_id (one per user) | registration_source in approved list; exactly one event per user_id; timestamp not in future | Start of lifecycle; acquisition analysis | Registrations; Cohort Retention (Day N) | Given a new account is created and committed, exactly one user_registered exists for that user_id with a registration_source from the approved list. | Given account creation fails or is rolled back, no user_registered is recorded. | To Be Verified | Depends on a stable user_id (AP-01). | To be confirmed by Engineering
AE-002 | task_started | Critical | Task attempt record created | User began an attempt at a task | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | task_activity_id | task_activity_id unique; task_id exists; one event per attempt | Denominator for completion rate | Feature Usage; Feature Adoption Rate; Task Starts; Task Completion Rate; Repeat Usage Rate; Provider Callback Reliability | When a task attempt record is created, exactly one task_started exists with a unique task_activity_id. | Retrying the same request does not create a second task_started for the same task_activity_id. | Proposed |  | To be confirmed by Engineering
AE-003 | task_completed | Critical | Completion has passed the applicable validation | A task attempt was validated as completed | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | task_activity_id | validation_status = passed; exactly one per task_activity_id; reward_unit in approved list; reward_amount not negative | Counts real completions only | Daily Active Users (DAU); Weekly Active Users (WAU); Monthly Active Users (MAU); Returning Users; Cohort Retention (Day N); Feature Adoption Rate; Task Completions; Task Completion Rate; Help-Center Engagement | When a valid task completion occurs, exactly one analytically usable completion event is recorded for the relevant task and user attempt, subject to the final engineering implementation and idempotency design. | A completion claim that fails validation produces task_failed and no task_completed. | Proposed | Emit when validation passes, not when the user claims completion (AP-03). | To be confirmed by Engineering
AE-004 | reward_credited | Critical | Wallet balance updated with the reward | A reward has actually been added to the wallet | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | reward_id | Exactly one per reward_id; wallet_transaction_id must exist; amount greater than 0 | Counts rewards actually given | Reward Transactions; Reward Credits; Reward Reversal Rate; Reward Activity by Feature; Pending Rewards; Net Reward Amount | When the wallet balance is updated with a reward, exactly one reward_credited exists carrying the wallet_transaction_id of the credit entry. | If the wallet write fails, no reward_credited is recorded. | Proposed | Emit only after the wallet write succeeds (AP-05). | To be confirmed by Engineering
AE-005 | reward_reversed | Critical | A credited reward is taken back | A previously credited reward was reversed | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | original_reward_id (one reversal per credited reward) | original_reward_id must refer to a credited reward; no second reversal of the same reward | Reward reliability | Reward Transactions; Reward Reversals; Reward Reversal Rate; Net Reward Amount | When a credited reward is taken back, one reward_reversed exists referencing its original_reward_id. | A second reversal of the same original reward is refused and produces no second event. | Proposed | Original reward is never edited; the reversal links to it. | To be confirmed by Engineering
AE-006 | wallet_transaction_created | Critical | Ledger entry created | A wallet entry was created | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | transaction_id (and idempotency_key where used) | wallet_transaction_id unique; amount greater than 0; direction agrees with transaction_type | Every balance change has a record | Wallet Transactions | When a ledger entry is created, one event exists with a unique transaction_id and an amount greater than 0. | Repeating a request with the same idempotency_key creates no second entry and no second event. | To Be Verified | An idempotency_key is recommended (AP-02). | To be confirmed by Engineering
AE-007 | wallet_transaction_reversed | Critical | Reversal entry created | An earlier wallet entry was reversed | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | transaction_id of the reversal entry | related_transaction_id exists and is not itself a reversal | Reversal tracking | Wallet Reversals | When a reversal entry is created, one event exists whose related_transaction_id points to an existing original entry. | A reversal that points to itself or to another reversal is refused and produces no event. | To Be Verified |  | To be confirmed by Engineering
AE-008 | withdrawal_requested | Critical | Withdrawal request created | User requested a withdrawal | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | withdrawal_id | withdrawal_id unique; requested_amount greater than 0; method in approved list | Start of withdrawal lifecycle | Daily Active Users (DAU); Weekly Active Users (WAU); Monthly Active Users (MAU); Returning Users; Cohort Retention (Day N); Feature Adoption Rate; Withdrawal Requests; Pending Withdrawals; Processing Time; Withdrawal Completion Rate; Pending Queue Age; Withdrawal Volume; Withdrawal Method Distribution; Help-Center Engagement | When a withdrawal request is stored, one event exists with a method from the approved list and requested_amount greater than 0. | A request refused before it is stored produces no withdrawal_requested. | To Be Verified | Whether the balance is held at request time is an open question (see the Wallet and Withdrawal specification). | To be confirmed by Engineering
AE-009 | withdrawal_completed | Critical | Payout finished | A withdrawal was paid out | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | withdrawal_id | Follows withdrawal_processing; one linked debit; completed_amount not above requested unless a fee rule exists | Payout output | Completed Withdrawals; Pending Withdrawals; Processing Time; Withdrawal Completion Rate; Withdrawal Volume; Withdrawal Method Distribution | When a payout finishes, one event exists with completed_amount and the linked wallet_transaction_id. | A withdrawal in rejected status never emits withdrawal_completed. | To Be Verified |  | To be confirmed by Engineering
AE-010 | user_logged_in | High | Login succeeds | A user has started an authenticated visit | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | event_id only (one per login) | user_id must exist; timestamp not before registration | Return behaviour; visit counts (kept separate from 'active') | Daily Visitors | Given a successful login, exactly one user_logged_in exists for that login and its user_id exists in Users. | A failed login attempt produces no user_logged_in. | Proposed | Login events may be absent for automatic sessions (A004). | To be confirmed by Engineering
AE-011 | onboarding_started | High | First onboarding screen shown | User has entered the onboarding flow | Frontend | event_timestamp = device time converted to UTC; the pipeline adds received_timestamp so clock drift can be measured. | user_id + onboarding_step (once per onboarding run) | onboarding_step in current flow list; once per user unless flow restarts | Onboarding funnel entry | Onboarding Completion Rate | When the first onboarding screen is shown to a registered user, one onboarding_started with the onboarding_step is recorded. | Re-opening the same step in the same run does not create a second event. | Proposed | Onboarding step list to be confirmed. | To be confirmed by Engineering
AE-012 | onboarding_completed | High | Final onboarding step done | User has finished onboarding | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | user_id (once per user) | Must follow onboarding_started; once per user | Activation proxy | Onboarding Completion Rate | When the final onboarding step is completed, one onboarding_completed exists and follows an onboarding_started for the same user. | No onboarding_completed exists for a user without an earlier onboarding_started. | Proposed | Treatment of skipped onboarding to be agreed. | To be confirmed by Engineering
AE-013 | account_status_changed | High | account_status updated by user, system or operations | An account moved from one status to another | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | user_id + changed_at + new_status | previous_status differs from new_status; values in approved status list | Track restrictions and closures | Account Status Mix | When account_status changes from A to B, one event exists with previous_status = A, new_status = B and the actor. | An update that leaves the status unchanged produces no event. | To Be Verified | Real status names must be mapped (A019). | To be confirmed by Engineering
AE-014 | task_failed | High | Attempt ends without validated completion | A task attempt failed or was abandoned | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | task_activity_id | failure_category in approved list; cannot follow task_completed for the same attempt | Explain drop-off and failures | Task Failure Mix | When an attempt ends failed or abandoned, one task_failed exists with a failure_category from the approved list. | No task_failed exists for a task_activity_id that has a task_completed. | Proposed |  | To be confirmed by Engineering
AE-015 | reward_pending | High | Reward created but not yet usable | A reward is held awaiting validation or confirmation | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | reward_id | reward_id unique; reward_amount greater than 0 | Pending reward queue | Reward Transactions; Pending Rewards | When a reward is created but not yet usable, one reward_pending exists with a pending_reason. | A reward credited immediately produces no reward_pending. | Proposed |  | To be confirmed by Engineering
AE-016 | daily_reward_claimed | High | Daily reward successfully claimed | User claimed the daily reward | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | user_id + claim_date | One per user per claim_date; reward_amount not negative | Daily habit measurement | Daily Active Users (DAU); Weekly Active Users (WAU); Monthly Active Users (MAU); Returning Users; Cohort Retention (Day N); Feature Adoption Rate; Streak Length; Help-Center Engagement | When a user claims the daily reward, one event exists with claim_date and streak_day. | A second claim on the same claim_date produces no second event. | Proposed |  | To be confirmed by Engineering
AE-017 | referral_created | High | Referral code or link created | A referral was created by a user | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | referral_id | referral_id unique; referring_user_id must exist | Referral funnel start | Referrals Created; Referral Conversion Rate | When a referral record is created, one referral_created exists with a unique referral_id. | A referral with a non-existent referring_user_id is refused and produces no event. | Proposed |  | To be confirmed by Engineering
AE-018 | referral_registered | High | Referred user completes sign-up | A referred user registered | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | referral_id | referred_user_id differs from referring_user_id; follows referral_created | Registration is not conversion | Referral Registrations; Referral Activation Rate | When a referred user registers, one referral_registered exists and referred_user_id differs from referring_user_id. | A self-referral produces no referral_registered. | Proposed |  | To be confirmed by Engineering
AE-019 | referral_activated | High | Referred user meets activation rule | A referred user became activated | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | referral_id | Follows referral_registered; once per referral_id | Quality of referrals | Referral Activations; Referral Activation Rate | When the activation rule is met, one referral_activated exists with the activation_rule_version applied. | No referral_activated exists for a referral without an earlier referral_registered. | To Be Verified | The activation rule is not yet agreed (A010, AP-07). | To be confirmed by Engineering
AE-020 | referral_converted | High | Referral meets success condition | A referral was successful | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | referral_id | Follows referral_activated unless rule says otherwise; once per referral_id | True referral success | Referral Conversions; Referral Conversion Rate | When the success condition is met, one referral_converted exists for that referral_id. | A second conversion for the same referral_id produces no event. | Proposed |  | To be confirmed by Engineering
AE-021 | wallet_transaction_completed | High | Ledger entry becomes final | A wallet entry was completed | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | transaction_id | Follows wallet_transaction_created; once per transaction | Settlement and balance integrity | Wallet Transactions; Credit Volume; Redemption Activity; Wallet Reconciliation Exceptions | When an entry becomes final, one completed event exists and follows the created event for the same transaction_id. | No completed event exists for an entry that failed. | To Be Verified |  | To be confirmed by Engineering
AE-022 | withdrawal_processing | High | Request enters review or processing | A withdrawal started processing | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | withdrawal_id | Follows withdrawal_requested; once per withdrawal | Processing time and queue | Pending Withdrawals; Pending Queue Age | When review or processing begins, one event exists and follows withdrawal_requested for the same withdrawal_id. | No second processing event is recorded for the same withdrawal_id. | To Be Verified |  | To be confirmed by Engineering
AE-023 | withdrawal_rejected | High | Request refused | A withdrawal was rejected | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | withdrawal_id | reason_category required; cannot follow withdrawal_completed | Understand friction | Pending Withdrawals; Rejected Withdrawals; Processing Time | When a request is refused, one event exists with a reason_category. | No withdrawal_rejected exists for a withdrawal that is already completed. | To Be Verified |  | To be confirmed by Engineering
AE-024 | withdrawal_reversed | High | Completed payout undone or returned | A completed withdrawal was reversed | Backend | event_timestamp = server time when the change was committed (UTC, ISO 8601). received_timestamp is added by the pipeline. | withdrawal_id | Must follow withdrawal_completed | Payout reliability | Reversed Withdrawals | When a completed payout is reversed, one event exists with a reason_category. | No withdrawal_reversed exists for a withdrawal that never completed. | To Be Verified |  | To be confirmed by Engineering
AE-025 | provider_callback_received | High | External provider reports a result (name to be agreed) | A provider callback arrived | Provider | event_timestamp = provider_event_time if supplied, otherwise callback_received_at; both are stored (UTC). | provider_name + provider_reference_id + provider_status | provider_reference_id present; stored separately from VELOOP status | Reliability of external providers | Provider Callback Reliability | When a provider callback arrives, one event exists storing provider_reference_id, provider_status and callback_received_at. | A repeated callback with the same provider_reference_id and status creates no second event. | To Be Verified | Event name to be agreed. | To be confirmed by Engineering

## Payload_Fields
Requirement ID | Event | Field | Data type | Required | Validation
AE-001 | user_registered | registration_source | enum | Yes | In approved list; 'unknown' instead of null
AE-001 | user_registered | registration_method | enum | No | In approved list
AE-001 | user_registered | referral_code_used | string | No | Matches an existing referral code or null
AE-001 | user_registered | campaign_id | string | No | In list or null
AE-001 | user_registered | country_code | string | No | Valid code; never precise location
AE-002 | task_started | task_activity_id | string | Yes | Unique; immutable; generated when the record is created
AE-002 | task_started | task_id | string | Yes | Must exist in Tasks
AE-002 | task_started | task_type | enum | Yes | In approved list
AE-002 | task_started | feature | enum | Yes | In approved list
AE-002 | task_started | provider_name | string | No | Required when validation_method = provider
AE-002 | task_started | provider_reference_id | string | No | Unique per provider
AE-002 | task_started | attempt_number | integer | No | Integer >= 1
AE-003 | task_completed | task_activity_id | string | Yes | Must exist in Task_Activity
AE-003 | task_completed | task_id | string | Yes | Must exist in Tasks
AE-003 | task_completed | task_type | enum | Yes | In approved list
AE-003 | task_completed | reward_amount | decimal | Yes | Not negative
AE-003 | task_completed | reward_unit | enum | Yes | Required when amount present
AE-003 | task_completed | validation_status | enum | Yes | In approved list
AE-003 | task_completed | reward_id | string | No | Must exist in Rewards
AE-003 | task_completed | provider_reference_id | string | No | Unique per provider
AE-004 | reward_credited | reward_id | string | Yes | Must exist in Rewards
AE-004 | reward_credited | reward_amount | decimal | Yes | Not negative
AE-004 | reward_credited | reward_unit | enum | Yes | Required when amount present
AE-004 | reward_credited | source_feature | enum | Yes | In approved list
AE-004 | reward_credited | wallet_transaction_id | string | Yes | Must exist in Wallet_Transactions
AE-004 | reward_credited | task_activity_id | string | No | Must exist in Task_Activity
AE-005 | reward_reversed | reward_id | string | Yes | Must exist in Rewards
AE-005 | reward_reversed | original_reward_id | string | Yes | Must exist in Rewards (not equal to the record's own id)
AE-005 | reward_reversed | reward_amount | decimal | Yes | Not negative
AE-005 | reward_reversed | reward_unit | enum | Yes | Required when amount present
AE-005 | reward_reversed | reason_category | enum | Yes | No free text
AE-005 | reward_reversed | wallet_transaction_id | string | Yes | Must exist in Wallet_Transactions
AE-006 | wallet_transaction_created | wallet_transaction_id | string | Yes | Unique; immutable; generated when the record is created
AE-006 | wallet_transaction_created | transaction_type | enum | Yes | In approved list
AE-006 | wallet_transaction_created | direction | enum | Yes | Agrees with transaction_type
AE-006 | wallet_transaction_created | amount | decimal | Yes | Greater than 0
AE-006 | wallet_transaction_created | unit | enum | Yes | One unit per entry
AE-006 | wallet_transaction_created | reference_id | string | Yes | Must exist in referenced table
AE-006 | wallet_transaction_created | source_feature | enum | Yes | In approved list
AE-006 | wallet_transaction_created | related_transaction_id | string | No | Must exist in Wallet_Transactions (not equal to the record's own id)
AE-006 | wallet_transaction_created | exchange_group_id | string | No | One debit and one credit
AE-007 | wallet_transaction_reversed | wallet_transaction_id | string | Yes | Must exist in Wallet_Transactions
AE-007 | wallet_transaction_reversed | related_transaction_id | string | Yes | Must exist in Wallet_Transactions (not equal to the record's own id)
AE-007 | wallet_transaction_reversed | amount | decimal | Yes | Greater than 0
AE-007 | wallet_transaction_reversed | unit | enum | Yes | One unit per entry
AE-007 | wallet_transaction_reversed | reason_category | enum | Yes | No free text
AE-008 | withdrawal_requested | withdrawal_id | string | Yes | Unique; immutable; generated when the record is created
AE-008 | withdrawal_requested | requested_amount | decimal | Yes | Greater than 0
AE-008 | withdrawal_requested | requested_unit | enum | Yes | In approved list
AE-008 | withdrawal_requested | method | enum | Yes | In approved list
AE-008 | withdrawal_requested | wallet_transaction_id | string | No | Must exist in Wallet_Transactions
AE-009 | withdrawal_completed | withdrawal_id | string | Yes | Must exist in Withdrawals
AE-009 | withdrawal_completed | method | enum | Yes | In approved list
AE-009 | withdrawal_completed | completed_amount | decimal | Yes | Required when completed
AE-009 | withdrawal_completed | requested_unit | enum | Yes | In approved list
AE-009 | withdrawal_completed | wallet_transaction_id | string | Yes | Must exist in Wallet_Transactions
AE-009 | withdrawal_completed | provider_reference_id | string | No | Unique per provider
AE-010 | user_logged_in | attempt_number | integer | No | Integer >= 1
AE-011 | onboarding_started | onboarding_step | string | Yes | Non-empty; no personal data
AE-012 | onboarding_completed | onboarding_step | string | Yes | Non-empty; no personal data
AE-012 | onboarding_completed | step_completed_count | integer | No | Whole number, 0 or more
AE-013 | account_status_changed | previous_status | enum | Yes | Differs from new_status
AE-013 | account_status_changed | new_status | enum | Yes | In approved list
AE-013 | account_status_changed | status_change_actor | enum | Yes | In approved list
AE-013 | account_status_changed | reason_category | enum | No | No free text
AE-014 | task_failed | task_activity_id | string | Yes | Must exist in Task_Activity
AE-014 | task_failed | task_id | string | Yes | Must exist in Tasks
AE-014 | task_failed | failure_category | enum | Yes | Required when failed or abandoned
AE-014 | task_failed | failure_detail_code | string | No | No personal data
AE-014 | task_failed | provider_name | string | No | Required when validation_method = provider
AE-014 | task_failed | provider_reference_id | string | No | Unique per provider
AE-015 | reward_pending | reward_id | string | Yes | Unique; immutable; generated when the record is created
AE-015 | reward_pending | reward_amount | decimal | Yes | Not negative
AE-015 | reward_pending | reward_unit | enum | Yes | Required when amount present
AE-015 | reward_pending | source_feature | enum | Yes | In approved list
AE-015 | reward_pending | pending_reason | enum | Yes | Required when pending
AE-015 | reward_pending | task_activity_id | string | No | Must exist in Task_Activity
AE-016 | daily_reward_claimed | claim_date | date | Yes | ISO 8601 date
AE-016 | daily_reward_claimed | streak_day | integer | Yes | Whole number, 0 or more
AE-016 | daily_reward_claimed | reward_amount | decimal | Yes | Not negative
AE-016 | daily_reward_claimed | reward_unit | enum | Yes | Required when amount present
AE-016 | daily_reward_claimed | reward_id | string | No | Must exist in Rewards
AE-017 | referral_created | referral_id | string | Yes | Unique; immutable; generated when the record is created
AE-017 | referral_created | referring_user_id | string | Yes | Must exist in Users
AE-017 | referral_created | referral_code_used | string | No | Matches an existing referral code or null
AE-017 | referral_created | campaign_id | string | No | In list or null
AE-018 | referral_registered | referral_id | string | Yes | Must exist in Referrals
AE-018 | referral_registered | referring_user_id | string | Yes | Must exist in Users
AE-018 | referral_registered | referred_user_id | string | Yes | Must exist in Users
AE-019 | referral_activated | referral_id | string | Yes | Must exist in Referrals
AE-019 | referral_activated | referred_user_id | string | Yes | Must exist in Users
AE-019 | referral_activated | activation_rule_version | string | Yes | Matches change log
AE-020 | referral_converted | referral_id | string | Yes | Must exist in Referrals
AE-020 | referral_converted | referring_user_id | string | Yes | Must exist in Users
AE-020 | referral_converted | referred_user_id | string | Yes | Must exist in Users
AE-020 | referral_converted | reward_id | string | No | Must exist in Rewards
AE-020 | referral_converted | wallet_transaction_id | string | No | Must exist in Wallet_Transactions
AE-021 | wallet_transaction_completed | wallet_transaction_id | string | Yes | Must exist in Wallet_Transactions
AE-021 | wallet_transaction_completed | transaction_type | enum | Yes | In approved list
AE-021 | wallet_transaction_completed | direction | enum | Yes | Agrees with transaction_type
AE-021 | wallet_transaction_completed | amount | decimal | Yes | Greater than 0
AE-021 | wallet_transaction_completed | unit | enum | Yes | One unit per entry
AE-021 | wallet_transaction_completed | transaction_status | enum | Yes | Value in the approved list
AE-022 | withdrawal_processing | withdrawal_id | string | Yes | Must exist in Withdrawals
AE-022 | withdrawal_processing | method | enum | Yes | In approved list
AE-022 | withdrawal_processing | provider_reference_id | string | No | Unique per provider
AE-023 | withdrawal_rejected | withdrawal_id | string | Yes | Must exist in Withdrawals
AE-023 | withdrawal_rejected | method | enum | Yes | In approved list
AE-023 | withdrawal_rejected | reason_category | enum | Yes | No free text
AE-024 | withdrawal_reversed | withdrawal_id | string | Yes | Must exist in Withdrawals
AE-024 | withdrawal_reversed | method | enum | Yes | In approved list
AE-024 | withdrawal_reversed | reason_category | enum | Yes | No free text
AE-024 | withdrawal_reversed | wallet_transaction_id | string | Yes | Must exist in Wallet_Transactions
AE-024 | withdrawal_reversed | provider_reference_id | string | No | Unique per provider
AE-025 | provider_callback_received | provider_name | string | Yes | Required when validation_method = provider
AE-025 | provider_callback_received | provider_reference_id | string | Yes | Unique per provider
AE-025 | provider_callback_received | provider_status | enum | Yes | Value in the approved list
AE-025 | provider_callback_received | callback_received_at | timestamp | Yes | ISO 8601 UTC
AE-025 | provider_callback_received | provider_event_time | timestamp | No | ISO 8601 UTC
AE-025 | provider_callback_received | task_activity_id | string | No | Must exist in Task_Activity

## Common_Payload
Field | Type | Required | Meaning
event_id | string | Yes | Unique key; a retry reuses it
event_name | string | Yes | Name from the catalogue
event_timestamp | timestamp (UTC) | Yes | When the fact happened
received_timestamp | timestamp (UTC) | Yes (added by pipeline) | When the pipeline received it
user_id | string | Yes | Stable user key
schema_version | string | Yes | Event definition version
platform | enum | Yes | android, ios, web
app_version | string | Yes | App version that emitted it
source | enum | Yes | frontend, backend, provider
session_id | string | Optional | Present only if session tracking exists

## General_Requirements
Requirement ID | Requirement | Description | Acceptance test | Priority | Status | Engineering response
AG-01 | Common payload on every event | Every event carries event_id, event_name, event_timestamp, user_id, schema_version, platform, app_version and source; session_id when session tracking exists; the pipeline adds received_timestamp. | Sample of events from each type: every one contains all common properties with valid types. | Critical | Proposed
AG-02 | UTC timestamps | All timestamps are ISO 8601 in UTC. Backend outcomes use the server clock, not the device clock. | A change made at a known server time appears with that time in UTC; no event has a local-time offset missing. | Critical | Proposed
AG-03 | Emit after commit | An event is emitted only after the business change is committed. A failed or rolled-back change emits nothing. | Force a failed write: no event exists. Complete a successful write: exactly one event exists. | Critical | Proposed
AG-04 | Retry-safe event_id | A retry of the same event reuses its event_id, so duplicates can be removed. | Send the same event twice: the analytics store holds one. | Critical | Proposed
AG-05 | Analytics never blocks users | Failure to deliver an event must not fail the user's action. Undelivered events are queued and retried. | Disable the analytics endpoint: user actions still succeed and events arrive after it returns. | High | Proposed
AG-06 | No personal data or secrets | No names, contact details, precise location, passwords, tokens, API keys or payment credentials appear in any payload. | Automated scan of sample payloads finds none of these. | Critical | Proposed
AG-07 | Schema versioning | schema_version is set on every event. A breaking change is a new version; existing consumers keep working. | Release a new version: old-version events still pass validation. | High | Proposed
AG-08 | Catalogue names only | Only event names in the Event Tracking Plan are emitted. Unknown names are rejected or quarantined at collection. | Send an unknown event_name: it is quarantined with rule DQ020. | High | Proposed
AG-09 | Environment separation | Test, simulated and production events are kept apart and never mixed. | Events from a test build never appear in the production stream. | Critical | Proposed
AG-10 | Single approved-value source | Enums (statuses, units, methods, categories) are defined once and shared by the app and the pipeline. | Changing an approved value in one place changes validation everywhere. | High | Proposed
AG-11 | Outcomes from the backend | Interactions (opened, viewed) may come from the frontend. Outcomes (completed, credited, reversed, status changes) come from the backend. | Outcome events show source = backend. | High | Proposed
AG-12 | Documented and logged changes | Every released event, property or rule change is recorded in the change log (Work Package Q). | Each change has a log entry with old and new definition. | Medium | Proposed

## Preconditions
Requirement ID | Pre-condition | Linked gap | Priority | Priority reason | Acceptance test | Engineering response
AP-01 | A stable, anonymous, immutable user_id exists for every account and survives device changes. | G01 | Critical | Without a stable user_id, one person can appear as several users | The same person on two devices has one user_id; an id is never reused.
AP-02 | Every wallet entry has a unique transaction_id, and writes are idempotent. | G02 | Critical | Without a stable transaction ID, reliable wallet deduplication cannot be guaranteed | Repeating a request produces one entry; no two entries share a transaction_id.
AP-03 | Task attempts are stored with a task_activity_id and the time validation finished. | G03 | Critical | All earning analytics depend on completion events | For any completed task there is one attempt row with started, claimed and completed times.
AP-04 | Reward units are defined and every reward and wallet entry carries exactly one unit. | G04 | Critical | Wrong totals would mislead management | No entry has a missing unit; sums by unit reconcile.
AP-05 | Activity and reward are separate records: a reward is credited only after the wallet write succeeds. | G05 | Critical | Overstated reward figures | A completed task with a failed wallet write shows no credited reward.
AP-06 | Each withdrawal state change is stored with its own timestamp. | G06 | High | Without state history, only the latest status is visible | For a completed withdrawal, requested, processing and final times all exist.
AP-07 | One activation definition is agreed and stored with a rule version. | G07 | High | Inflated referral success | Every activated referral shows the rule version applied.
AP-08 | Failures are recorded with a category, not only a generic status. | G09 | High | Needed to act on problems, not just count them | Every failed or rejected record has a category from the approved list.
AP-09 | The provider's reference id is stored for every externally driven activity. | G10 | High | External systems are outside VELOOP control | Provider-validated attempts carry a provider_reference_id.
AP-10 | Timestamps are stored in UTC with a known format. | G11 | High | Wrong day bucket changes DAU and streaks | No stored timestamp lacks a timezone or has an unreadable format.
AP-11 | Product confirms which features are live and which are planned. | G13 | High | Wasted engineering effort and empty dashboards | The event list is trimmed to live and imminent features.
AP-12 | A data store and event collection route are chosen and documented. | G14 | High | Pipeline design depends on it | Events from a test action arrive in the raw store.