## README
VELOOP REWARDS - Task 01 ¦ Final Implementation Backlog
The backlog is Proposed: it has not been agreed with Engineering or Product. Priorities and order may change once VELOOP confirms the facts in the Assumption Register. No simulated or real VELOOP statistics are included.
- Priority comes from the readiness gaps and assumption risks. Every priority has a reason, as the brief requires.
- Wave shows build order: wave 1 has no dependencies, wave 2 depends only on wave 1, and so on.
- Stage follows the brief: Pre-launch means needed before production reporting is relied on; Post-launch means it can follow.
- Milestones M1 to M7 are those in the Pipeline Proposal; J and K are the dataset-dependent work packages.
- Items of type Decision or Confirmation need an answer, not engineering effort, and are the quickest to close.
- Critical Path = Yes marks a High or lower item that gates a Critical item, so it should not slip even though its own priority is lower.
Open questions:
- Does Engineering agree the order and dependencies?
- Who will own backlog tracking day to day?
- Which Product decisions can be taken in the first conversation?
- Will the remaining datasets be provided so profiling, the audit and the KPI test can be re-run?
Live counts
Backlog items | 43
Critical | 6
Pre-launch | 33
Post-launch | 10
Wave 1 (no dependencies) | 17

## Backlog
ID | Priority | Requirement | Reason | Dependency | Owner | Stage | Type | Wave | Milestone | Sources | Closing Evidence | Linked Documents | Status | Critical Path
BL-01 | Critical | Confirm which of the 42 proposed events already exist, who emits each, and whether each comes from the frontend or backend | Critical - Without registered, task, reward, wallet and withdrawal events, none of the core KPIs can be computed from production data | None | Engineering | Pre-launch | Confirmation | 1 | M1 | RG-01, RG-02, A001, A021 | Engineering lists emitted events, with a sample record and the emitter for each | Event Tracking Plan; Developer Handoff | Proposed (not yet agreed with Engineering or Product) | Critical item
BL-02 | Critical | Guarantee a stable, immutable user_id and a unique transaction_id on every wallet entry | Critical - Without a stable transaction ID, reliable wallet transaction deduplication cannot be guaranteed; without a stable user_id, cross-event analysis breaks | None | Engineering | Pre-launch | Engineering build | 1 | M1 | RG-04, AP-01, AP-02, A003, A005 | Same user keeps one user_id across devices; no two wallet entries share a transaction_id | Logical Data Model; Developer Handoff | Proposed (not yet agreed with Engineering or Product) | Critical item
BL-03 | Critical | Confirm the wallet ledger design: append-only or edited in place, when withdrawal amounts are held, fees and limits, cancellation, and redemption and exchange records | Critical - If balances are edited in place, balance reconciliation and reversals cannot be trusted | None | Engineering / Product | Pre-launch | Confirmation | 1 | M1 | A026, A027, A028, A029, A030 | Written answers recorded in the assumption register | Wallet and Withdrawal Specification; Logical Data Model | Proposed (not yet agreed with Engineering or Product) | Critical item
BL-04 | Critical | Agree and test an idempotency design for event and wallet writes | Critical - Retries could create duplicate events and duplicate wallet credits | BL-02 | Engineering | Pre-launch | Engineering build | 2 | M1 | RG-19, AG-03, AG-04, A023 | A repeated request produces one event and one wallet entry | Developer Handoff | Proposed (not yet agreed with Engineering or Product) | Critical item
BL-05 | Critical | Implement the common payload and general engineering requirements (AG-01 to AG-12) | Critical - Without a common payload, events cannot be deduplicated, ordered or traced to a user | BL-16, BL-04, BL-10 | Engineering | Pre-launch | Engineering build | 3 | M2 | AG-01 to AG-12 | Sampled events pass every general acceptance test | Developer Handoff; Event Tracking Plan | Proposed (not yet agreed with Engineering or Product) | Critical item
BL-06 | Critical | Instrument the 9 Critical events to the developer handoff specification (AE-001 to AE-009) | Critical - Core KPIs for registrations, tasks, rewards, wallet and withdrawals depend on them | BL-02, BL-04, BL-05, BL-15, BL-21, BL-03 | Engineering | Pre-launch | Engineering build | 5 | M2 | AE-001 to AE-009 | Each event passes its positive and negative acceptance test | Developer Handoff; Event Tracking Plan | Proposed (not yet agreed with Engineering or Product) | Critical item
BL-07 | High | Decide which events make a user 'active' and the activity window | High - DAU, WAU, MAU, returning and inactive users all depend on it | None | Product | Pre-launch | Decision | 1 | M1 | RG-09, A024 | Decision recorded in the change log | KPI Catalogue; Referral and Engagement | Proposed (not yet agreed with Engineering or Product) | No
BL-08 | High | Agree one activation definition for users and referrals, stored with a rule version | High - Referral activation and conversion would be reported on an unstable rule | None | Product | Pre-launch | Decision | 1 | M1 | RG-10, AP-07, A010 | One rule agreed, with a version number | Referral and Engagement; KPI Catalogue | Proposed (not yet agreed with Engineering or Product) | No
BL-09 | High | Define reward units and any conversion between them | High - Amounts in different units cannot be added or compared | None | Product / Finance | Pre-launch | Decision | 1 | M1 | RG-12, AP-04, A002 | Unit list and conversion rule confirmed | Earning and Reward; Wallet and Withdrawal | Proposed (not yet agreed with Engineering or Product) | Yes
BL-10 | High | Standardise UTC timestamps and agree the timezone and week and month boundaries | High - A wrong day or a missing timezone changes daily metrics and streaks | None | Engineering / Product | Pre-launch | Engineering build | 1 | M1 | RG-11, RG-22, AP-10, A012 | Sample records show UTC ISO 8601; boundaries written into the KPI Catalogue | KPI Catalogue; Developer Handoff | Proposed (not yet agreed with Engineering or Product) | Yes
BL-11 | High | Confirm which features are live and which are planned | High - Events built for features that do not exist waste effort and leave dashboards empty | None | Product | Pre-launch | Confirmation | 1 | M1 | G13, A008 | Feature list with live, planned or not planned | Source and Verification Register; Coverage Matrix | Proposed (not yet agreed with Engineering or Product) | No
BL-12 | High | Obtain the remaining simulated datasets (task activity, rewards, wallet, withdrawals, referrals, feature events) and re-run the profiling, relationship tests, KPI test and quality audit | High - Only the Users data has been tested; most KPIs and 21 of the 39 quality rules could not be tested without the other datasets | None | Mentor / Product team; Data Analyst | Pre-launch | Analysis (needs datasets) | 1 | J and K | RG-13, A046 | All datasets profiled and the audit and KPI test re-run, with issue counts by rule ID | Simulated Data Profiling; Data Quality Audit; KPI Catalogue | Proposed (not yet agreed with Engineering or Product) | No
BL-13 | High | Fix derived fields, counters and consent consistency: compute derived values in the analytics layer, check counters against each other, and enforce 'marketing opt-in requires accepted consent' | High - Contradictory derived values, counters and consent would corrupt activity and consent metrics | None | Engineering / Product | Pre-launch | Engineering build | 1 | M3 | RG-31, A047, A049, A050, DQ040 to DQ042 | DQ040 to DQ042 pass on a new extract | Data Quality Audit; Quality Framework | Proposed (not yet agreed with Engineering or Product) | No
BL-14 | High | Name data owners and stewards, and set up access grants and logging | High - Restricted fields (6) need owners and grants before data flows | None | Product / Engineering | Pre-launch | Governance | 1 | M3 | RG-24, A037 | Named owners and an access log | Privacy and Governance | Proposed (not yet agreed with Engineering or Product) | No
BL-15 | High | Confirm fields and the approved lists (statuses, units, methods, categories) in one reference table | High - Allowed values are placeholders, so validation rules cannot be finalised | BL-09, BL-01 | Engineering / Product | Pre-launch | Confirmation | 2 | M1 | RG-07, A002, A006, A022 | Fields confirmed; lists stored in a shared reference table | Data Dictionary; Quality Framework | Proposed (not yet agreed with Engineering or Product) | Yes
BL-16 | High | Choose the event collection route and the analytics data store | High - Events have nowhere to land and the pipeline cannot start | BL-01 | Engineering | Pre-launch | Decision | 2 | M2 | RG-20, AP-12, A011 | Route and store documented; a test event reaches the raw zone | Pipeline Proposal | Proposed (not yet agreed with Engineering or Product) | Yes
BL-17 | High | Store each withdrawal state change with its own timestamp | High - Without per-state times, only the latest status is visible and processing time cannot be measured | BL-01 | Engineering | Pre-launch | Engineering build | 2 | M2 | RG-05, AP-06, A006, A007 | A sample withdrawal shows requested, processing and final timestamps | Wallet and Withdrawal Specification | Proposed (not yet agreed with Engineering or Product) | No
BL-18 | High | Store the provider's reference id for every externally driven activity, and agree the wait times for 'abandoned' and 'tracking_failed' | High - Third-party earning cannot be reconciled and completions may be understated | BL-01 | Engineering / Product | Pre-launch | Engineering build | 2 | M2 | RG-21, AP-09, A009, A042 | Provider-validated attempts carry a reference id; wait times recorded | Earning and Reward; KPI Catalogue | Proposed (not yet agreed with Engineering or Product) | No
BL-19 | High | Confirm that operational tables can be read from a replica or export without affecting the live product | High - The table extract flow depends on it | BL-16 | Engineering | Pre-launch | Confirmation | 3 | M2 | A033, A011 | Test extract completes with no impact on the product | Pipeline Proposal | Proposed (not yet agreed with Engineering or Product) | No
BL-20 | High | Separate simulated and production data and block simulated loads into production | High - Mixing simulated and production data would produce false results | BL-16 | Data Analyst / Engineering | Pre-launch | Engineering build | 3 | M2 | RG-30, DQ039 | Simulated data sits in a labelled separate zone and cannot load into production tables | Pipeline Proposal; Quality Framework | Proposed (not yet agreed with Engineering or Product) | No
BL-21 | High | Stand up the collection endpoint, the raw zone and the quarantine table | High - Valid events must be stored untouched and bad events held, not lost | BL-16, BL-05 | Engineering | Pre-launch | Engineering build | 4 | M2 | Pipeline Proposal; DQ001 to DQ006 | Valid events reach raw_events; a malformed event reaches quarantine with a rule ID | Pipeline Proposal; Quality Framework | Proposed (not yet agreed with Engineering or Product) | Yes
BL-22 | High | Instrument the 16 High events (AE-010 to AE-025) | High - Onboarding, failure, referral, pending reward and withdrawal lifecycle KPIs depend on them | BL-06, BL-08, BL-17, BL-18, BL-11 | Engineering | Pre-launch | Engineering build | 6 | M6 | AE-010 to AE-025 | Each event passes its positive and negative acceptance test | Developer Handoff; Event Tracking Plan | Proposed (not yet agreed with Engineering or Product) | No
BL-23 | High | Build transformation, quality rules and quarantine handling for the Critical events | High - Quality must be a pipeline stage so bad records never reach KPIs | BL-06, BL-21, BL-15, BL-10 | Data Analyst | Pre-launch | Engineering build | 6 | M3 | DQ001 to DQ039 | Rules run on test data and failures land in quarantine | Quality Framework; Pipeline Proposal | Proposed (not yet agreed with Engineering or Product) | No
BL-24 | High | Build the first dashboards: Executive Overview, Withdrawals and Wallet | High - Management needs reporting, but dashboards need confirmed events and clean data first | BL-06, BL-23, BL-34, BL-36, BL-07 | Data Analyst | Post-launch | Engineering build | 7 | M4 | RG-16 | Dashboards show only governed data with 'data as of' and quality status | Dashboard Blueprint | Proposed (not yet agreed with Engineering or Product) | No
BL-25 | High | Produce the first report from governed production data | High - No figure can be relied on until the layers below exist | BL-24 | Data Analyst / Product | Post-launch | Engineering build | 8 | M4 | RG-29, A021 | A report reconciles to the raw zone and passes the quality rules | Dashboard Blueprint; KPI Catalogue | Proposed (not yet agreed with Engineering or Product) | No
BL-26 | Medium | Decide which user attributes are collected for analytics (age, gender, state, city, consent, email verification) and keep personal-looking fields out of the analytics layer | Medium - Data minimisation: personal fields that no KPI needs add privacy risk without benefit | None | Product / Legal | Pre-launch | Decision | 1 | M3 | A048, RG-24 | Attribute list agreed; personal fields excluded from the analytics layer | Data Dictionary; Privacy and Governance | Proposed (not yet agreed with Engineering or Product) | No
BL-27 | Medium | Assign the quarantine triage owner and cadence | Medium - Quarantined records stay unresolved and KPIs stay incomplete | None | Data Analyst / Product | Pre-launch | Governance | 1 | M3 | RG-15, A034 | Named owner and cadence recorded | Quality Framework; Privacy and Governance | Proposed (not yet agreed with Engineering or Product) | No
BL-28 | Medium | Agree freshness, volume, clock-tolerance and late-arrival limits | Medium - Monitoring rules need limits to alert on | None | Engineering / Data Analyst | Pre-launch | Decision | 1 | M5 | RG-14, A035 | Limits written into the quality framework | Quality Framework | Proposed (not yet agreed with Engineering or Product) | No
BL-29 | Medium | Get Legal guidance on retention, deletion and consent, and set a retention period per zone | Medium - Raw data is append-only, so deletion requests need a designed process | None | Legal / Product | Pre-launch | Governance | 1 | M3 | RG-25, A016, A036 | Written Legal guidance and a retention period per zone | Privacy and Governance | Proposed (not yet agreed with Engineering or Product) | No
BL-30 | Medium | Review the document set with Product and Engineering and update statuses | Medium - Statuses stay Proposed until the VELOOP team confirms them | None | Data Analyst | Pre-launch | Governance | 1 | M1 | RG-27, A018 | Review notes and updated statuses | All documents | Proposed (not yet agreed with Engineering or Product) | No
BL-31 | Medium | Confirm whether a pending reward state and task attempts are stored | Medium - Pending Rewards and Task Completion Rate depend on them | BL-01 | Engineering | Pre-launch | Confirmation | 2 | M1 | RG-23, G05, A020, A031 | Engineering confirms both | Earning and Reward; Logical Data Model | Proposed (not yet agreed with Engineering or Product) | No
BL-32 | Medium | Confirm account statuses, onboarding steps and referral rules (one referrer per user, closing) | Medium - Account and referral KPIs need real values | BL-01 | Product / Engineering | Pre-launch | Confirmation | 2 | M1 | A019, A025 | Lists and rules recorded in the dictionary | User Analytics; Referral and Engagement | Proposed (not yet agreed with Engineering or Product) | No
BL-33 | Medium | Compare the logical data model with VELOOP's real tables | Medium - The model follows the brief, not the product, so some entities may change | BL-01 | Data Analyst | Pre-launch | Analysis | 2 | M3 | RG-06, A011, A031 | Differences logged and the model updated | Logical Data Model | Proposed (not yet agreed with Engineering or Product) | No
BL-34 | Medium | Choose the BI option | Medium - Aggregated-only access and refresh depend on the tool | BL-14 | Product / Data Analyst | Pre-launch | Decision | 2 | M4 | RG-17, A032 | Tool chosen against the dashboard blueprint and access model | Dashboard Blueprint; Privacy and Governance | Proposed (not yet agreed with Engineering or Product) | No
BL-35 | Medium | Confirm how registration source is captured, whether session ids are adopted, and whether a support system records issue categories | Medium - Acquisition, session and support KPIs depend on them | BL-01 | Engineering | Post-launch | Confirmation | 2 | M6 | G08, G12, G15, A004, A014, A015 | Written confirmation of each | User Analytics; KPI Catalogue | Proposed (not yet agreed with Engineering or Product) | No
BL-36 | Medium | Confirm or label each To Be Verified KPI on dashboards | Medium - Showing unverified KPIs without a label would overstate certainty | BL-07, BL-08, BL-03, BL-31 | Data Analyst | Post-launch | Governance | 3 | M4 | RG-18, A010, A013, A029, A030 | Each KPI confirmed or labelled | KPI Catalogue; Dashboard Blueprint | Proposed (not yet agreed with Engineering or Product) | No
BL-37 | Medium | Build monitoring and the pipeline health view | Medium - Problems should be noticed before users see wrong numbers | BL-23, BL-28 | Engineering / Data Analyst | Pre-launch | Engineering build | 7 | M5 | Pipeline Proposal | A forced failure produces an alert and a health view entry | Pipeline Proposal | Proposed (not yet agreed with Engineering or Product) | No
BL-38 | Medium | Specify and instrument the Medium and Low events | Medium - Full coverage of features and dashboards needs them | BL-22 | Data Analyst / Engineering | Post-launch | Engineering build | 7 | M6 | RG-03, A044 | Handoff requirements written and events pass tests | Developer Handoff; Event Tracking Plan | Proposed (not yet agreed with Engineering or Product) | No
BL-39 | Low | Agree change approvers, the overlap period and the notice period for breaking changes | Low - The change process works without them at first | None | Product | Post-launch | Governance | 1 | M7 | RG-28, A040, A041 | Roles and periods recorded | Change Management | Proposed (not yet agreed with Engineering or Product) | No
BL-40 | Low | Confirm country-level geography is available at registration | Low - Needed for the geographic view on the User Analytics dashboard | BL-01 | Engineering | Post-launch | Confirmation | 2 | M6 | A045 | Written confirmation | Dashboard Blueprint | Proposed (not yet agreed with Engineering or Product) | No
BL-41 | Low | Add real, sanitised example formats to the data dictionary | Low - Formats matter for validation but do not block design | BL-15 | Engineering | Post-launch | Documentation | 3 | M6 | RG-08, A022 | Examples added | Data Dictionary | Proposed (not yet agreed with Engineering or Product) | No
BL-42 | Low | Set the small-group suppression size and the access review cadence | Low - Needed for safe aggregated reporting but not blocking | BL-34, BL-14 | Product | Post-launch | Decision | 3 | M7 | RG-26, A038, A039 | Values agreed | Privacy and Governance | Proposed (not yet agreed with Engineering or Product) | No
BL-43 | Low | Review scale triggers and add Phase 2 components only where a trigger is met | Low - Avoid infrastructure added only because it sounds professional | BL-37 | Engineering / Data Analyst | Post-launch | Governance | 8 | M7 | Pipeline Proposal (scale triggers) | Each added component names its trigger | Pipeline Proposal | Proposed (not yet agreed with Engineering or Product) | No

## Summary_Priority_Stage
Priority | Pre-launch | Post-launch | Total
Critical | 6 | 0 | 6
High | 17 | 2 | 19
Medium | 10 | 3 | 13
Low | 0 | 5 | 5
Total | 33 | 10 | 43

## Summary_Wave
Wave | Items
1 | 17
2 | 11
3 | 6
4 | 1
5 | 1
6 | 2
7 | 3
8 | 2

## Summary_Type
Type | Items
Analysis | 1
Analysis (needs datasets) | 1
Confirmation | 9
Decision | 8
Documentation | 1
Engineering build | 16
Governance | 7