## README
VELOOP REWARDS - Task 01 ¦ Work Package O: Data Pipeline & Operating Model
Everything here is Proposed or To Be Verified. Nothing is claimed to exist in VELOOP today. No thresholds are invented; limits are 'to be agreed'. No simulated or real VELOOP statistics are included.
Design principles:
- Reuse before buying: start with what VELOOP already runs and add a component only when a named trigger is met.
- Keep raw data untouched and append-only, so any result can be rebuilt and any correction traced.
- Every transformation is safe to re-run, so a failed job is fixed by running it again, not by editing data.
- One definition per KPI: dashboards read the analytics layer, which implements the KPI Catalogue and nothing else.
- Quality is a pipeline stage, not a later clean-up: failing records are quarantined with a rule ID, never deleted.
- Simulated and production data stay in separate zones and are never silently mixed.
- Fewer moving parts: each extra tool adds cost, maintenance and failure points, so it needs an owner and a reason.
Cost principles:
- Reuse the existing database, hosting and tools first.
- Prefer free, open-source or already-licensed tools for Phase 1.
- Every paid or managed component must point to a trigger above and have a named decision owner.
- Count maintenance, not only purchase cost: fewer tools means fewer failures to look after.
- No component is added because it sounds professional.
RACI key: R responsible, A accountable (one per row), C consulted, I informed.
Tool examples are kinds of option, not a decision; the choice depends on VELOOP's existing stack (A011).
Open questions:
- What database, hosting and tools does VELOOP already run? This decides what Phase 1 reuses (A011).
- Which BI option will be used? The design is tool-neutral.
- Who owns triage of the quarantine table and how often?
- What freshness, volume and delay limits apply? (None are set here.)
- Can operational tables be read from a replica or export without affecting the live product?
- What retention period applies to raw data under the privacy rules? (Work Package P)

## Components
Component | What It Does | Phase 1: start simple | Phase 2: only when justified | Inputs | Outputs | Owner | Status
Source systems | The places data originates | Use what exists: the app, backend services, the operational database and third-party providers. Their current state is unknown (A011) | Add sources only as new features launch | User and system activity | Events and operational tables | Engineering | To Be Verified
Event producers | Emit events from the app | Backend emits outcome events after commit; frontend emits a small set of interaction events; provider callbacks are received by the backend and emitted from there | Client SDK with an offline queue | Business actions | Events with the common payload | Engineering | Proposed
Collection | Receive and check events | One collection endpoint (or a write to an events table by the backend) that checks the common payload, catalogue name, ID and timestamp, and de-duplicates on event_id | A managed queue or stream to absorb bursts | Events | Valid events to raw; rejects to quarantine | Engineering | Proposed
Storage | Where analytics data lives | A separate schema or database from production tables, using the database engine VELOOP already runs; regular backups | A dedicated warehouse, with object storage for raw files | Valid events, table extracts | Stored raw, clean and analytics data | Engineering / Data | Proposed
Raw layer | Hold exactly what arrived | raw_events and dated raw_table_extracts; append-only; received_timestamp added; never edited | Raw files partitioned by date | Collection output, table extracts | Untouched history | Data Analyst | Proposed
Transformation | Standardise, validate and model | Scheduled SQL scripts or views run in a fixed order; each safe to re-run | A SQL modelling tool with tests and generated documentation; an orchestrator | Raw layer, reference data | Clean entity tables; quarantine | Data Analyst | Proposed
Quality checks | Apply the quality rules | One SQL check per rule ID (DQ001 to DQ039) writing to a results table and the quarantine table | Automated test framework with alert integration | Raw and clean data | Pass or fail per rule; quarantined records | Data Analyst / Engineering | Proposed
Analytical layer | Business-ready tables | Clean entity tables plus views that implement each KPI formula | Materialised tables where views are slow | Clean tables | Tables and KPI views for dashboards | Data Analyst | Proposed
Dashboard | Show results | Any BI option that reads only the analytics views (a spreadsheet, an open-source BI tool or a hosted one); decision pending | Governed BI with row-level security | Analytics layer | 7 dashboards | Data Analyst / Product | To Be Verified
Refresh | Keep data current | Daily batch in a fixed run order (see run order) | More frequent refresh only for a dashboard where a named decision needs it | Schedule | Fresh tables and 'data as of' time | Data Analyst | Proposed
Monitoring | Notice problems early | A job log, a freshness check, a volume check, quarantine counts and reconciliation results summarised in one pipeline health view | Alerting tool with on-call routing | Job logs, rule results | Alerts to owners; health view | Engineering / Data | Proposed
Failure handling | Recover safely | Re-run idempotent jobs; dashboards show the last good data with a banner; a short runbook per failure | Automatic retries | Failure signals | Recovered data; incident note | Engineering / Data | Proposed
Ownership | Make someone responsible | Named owner per component, a RACI table and a change log (Work Package Q) | A data team with defined roles | Roles | Accountability | Product / Management | Proposed

## Data_Flows
Flow | From | To | Content | Method (Phase 1) | Frequency | Notes
F1 Events | Frontend, backend | Collection, then raw_events | Feature events with the common payload | HTTP endpoint or events table | As they happen (batched delivery allowed) | Rejects go to quarantine
F2 Table extracts | Operational database | raw_table_extracts | Users, Tasks, Task_Activity, Rewards, Wallet, Withdrawals, Referrals, Support | Scheduled read from a replica or export, never from the live write path where avoidable | Daily | Dated copies keep history; no edits
F3 Provider callbacks | Third-party providers | Backend, then F1 | Provider status and reference id | Backend receives the callback and emits provider_callback_received | As they happen | Missing callbacks stay 'unconfirmed' until the agreed wait passes
F4 Reference data | Product and Operations | Collection and transformation | Approved lists, event catalogue, data dictionary | One shared reference table or file under version control | On change | One source for app and pipeline (AG-10)
F5 Quarantine | Collection and transformation | Quarantine table | Records failing a rule, with rule ID and reason | Insert with raw reference | With each run | Triage owner assigned (open question)
F6 Metrics and alerts | All stages | Pipeline health view; owners | Job status, freshness, volume, quarantine and reconciliation results | Results table and summary message | Each run | Thresholds to be agreed

## Zones
Zone | Contents | Can be changed? | Who reads | Retention
Simulated (separate) | Simulated test datasets, each labelled 'SIMULATED DATA - CREATED FOR ANALYTICAL TESTING' | Rebuilt from documented generation method | Data Analyst, Intern (approved datasets) | Until replaced by governed production data; never merged silently
Raw | raw_events, raw_table_extracts | Never; append-only | Engineering, Data Analyst | To be agreed with Product (privacy)
Quarantine | Records that failed a rule | Status and resolution notes only | Data Analyst, Engineering | Until resolved, then per policy
Clean | Standardised, validated entity tables | Rebuilt by transformation | Data Analyst | To be agreed
Analytics | Entity tables and KPI views | Rebuilt by transformation | Data Analyst; aggregated to Product and Operations | To be agreed
Reporting | Dashboard extracts and shared reports | Rebuilt on refresh | Per access model (Work Package P) | Per report

## Run_Order
Step | Job | Depends On | If It Fails
1 | Ingest events and table extracts into the raw zone | - | Stop; alert; dashboards keep the last good data
2 | Raw checks: freshness, late arrivals, volume (DQ036 to DQ038) | 1 | Pause downstream steps and alert
3 | Transform and validate (DQ001 to DQ029); quarantine failures | 2 | Quarantine bad rows; fail the job only on a structural break; re-run after the fix
4 | Reconciliation checks (DQ030 to DQ034) | 3 | Alert owners; flag the affected KPIs on dashboards
5 | Build the analytics layer and KPI views | 4 | Keep the previous version; alert
6 | Refresh dashboards and set the 'data as of' banner | 5 | Show the last good data with a warning banner
7 | Publish the pipeline health summary | 1 to 6 | Alert Engineering if it cannot publish

## Monitoring
Monitor | What It Measures | Alert Condition | Alert Goes To | Related Rule or KPI
Job status | Did each step finish? | Any step fails or does not start | Engineering, Data Analyst | Run order
Freshness | Age of the latest received event and extract | Older than the agreed limit (to be agreed) | Engineering | DQ036
Volume | Rows received per day versus the recent pattern | Outside the agreed band (to be agreed) | Engineering | DQ038
Late arrivals | Delay between event and receipt | Above the agreed tolerance (to be agreed) | Engineering | DQ037, KPI T03
Quarantine | Records held per rule | Any Critical rule hit, or a rising rate | Data Analyst | Quality metrics
Reconciliation | Reward, wallet and withdrawal agreement | Any exception | Data Analyst, Finance | DQ030 to DQ032, KPI T01
Schema drift | Unknown event names, versions or columns | Any appearance | Engineering | DQ020, DQ021, DQ023
Provider reliability | Callbacks received within the agreed wait | Rising share missing | Engineering | KPI T02
Dashboard refresh | Did every dashboard update? | Any failure | Data Analyst | Run order step 6
Storage growth | Size of raw and analytics data | Growth beyond what the plan assumes (to be agreed) | Engineering | Scale triggers

## Failure_Handling
Failure | How It Is Detected | Immediate Handling | Recovery | Owner
Collection endpoint unavailable | Delivery errors; volume drop | The app queues and retries; the user's action is never blocked (AG-05) | Events arrive on retry; check raw counts against the backend | Engineering
Duplicate events | event_id repeats (DQ019) | Keep the first; count and log the rest | None needed beyond the log | Engineering
Malformed or unknown events | Collection rules (DQ003 to DQ006, DQ020, DQ022) | Quarantine with rule ID | Fix the producer, then reprocess from quarantine | Engineering
Late events | Delay above tolerance (DQ037) | Flag; restate the affected period | Re-run transformation for that period | Data Analyst
Transformation job fails | Job status | Dashboards keep the last good data and show a banner | Fix and re-run; jobs are safe to repeat | Data Analyst
Operational extract fails | Missing dated copy | Alert; reuse the previous copy with a banner | Re-run the extract | Engineering
Provider callback missing | Provider reliability monitor | Record stays 'unconfirmed' | Reconcile with the provider report; mark tracking_failed after the agreed wait | Engineering
Wallet reconciliation break | DQ030 to DQ032 | Alert Finance and Engineering; flag affected KPIs | Investigate the entries; correct with a reversal or adjustment entry, never an edit | Data Analyst
Bad data discovered after publishing | Report or quality check | Withdraw or caveat the figure | Rebuild from the raw zone | Data Analyst
Schema change from a release | Schema drift monitor | Unknown versions quarantined | Update the catalogue and rules, then reprocess | Engineering / Data
Simulated data enters production | DQ039 | Block the load | Remove and reload from the governed source | Data Analyst

## RACI
Responsibility | Engineering | Data Analyst | Product | Operations / Finance
Event emission and instrumentation | A/R | C | C | I
Event catalogue and definitions | C | R | A | C
Approved value lists | R | C | A | C
Collection and raw storage | A/R | C | I | I
Transformation and clean tables | C | A/R | I | I
Quality rules and quarantine triage | R | A | I | C
KPI definitions | I | R | A | C
Dashboards | I | R | A | C
Pipeline monitoring and alerts | R | A | I | I
Access control and privacy | R | C | A | C
Change log | C | R | A | I

## Scale_Triggers
Trigger | Signal | Response (Phase 2 step)
Analytics queries slow the production database | Production slowdown that lines up with analytics runs | Move analytics to a separate database or warehouse
Events are lost in bursts | Gaps between backend records and raw events | Add a queue or buffer
Daily jobs overrun the refresh window | Dashboards not ready when needed | Make builds incremental; add an orchestrator
A decision needs fresher data | A named decision cannot wait for next-day data | Raise refresh for that dashboard only
Several people change the models | Conflicting or unreviewed changes | Use version control and review; a SQL modelling tool
Roles need row-level separation | Access model needs it (Work Package P) | Governed BI with role-based access
Provider data must be merged regularly | Manual provider reconciliation takes recurring effort | Dedicated provider ingestion

## Tool_Examples
Layer | Phase 1 (example kind) | Phase 2 (example kind)
Collection | An endpoint in the existing backend, or writes to an events table | A managed event collector or queue
Storage | A separate schema in the database VELOOP already runs | A cloud warehouse with object storage
Transformation | SQL scripts and views run by a scheduler | A SQL modelling tool with tests, plus an orchestrator
Dashboard | A spreadsheet or an open-source BI tool | A hosted or governed BI service

## Milestones
Milestone | Outcome | Depends On | Backlog link
M1 | Stable user_id, transaction_id, UTC timestamps and the common payload agreed | Engineering decisions (AP-01, AP-02, AP-10) | Critical pre-conditions
M2 | Collection endpoint and raw zone receiving Critical events | M1 | Event tracking, AG-01 to AG-04
M3 | Transformation, quality rules and quarantine running for Critical events | M2, approved lists | Data quality checks
M4 | Analytics layer and first dashboards: Executive Overview, Withdrawals, Wallet | M3 | Dashboard blueprint
M5 | Monitoring and the pipeline health view | M3 | Monitoring
M6 | High priority events, remaining dashboards | M4 | Event tracking, dashboards
M7 | Review scale triggers; add Phase 2 components only where triggered | M5 | Scale triggers